## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | team-project-2181-swen-261-07-c-null
Testing Team Name | -
User Story Name: | User Story Description: (highlight green for pass, red for fail) | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
Start a Game | As a Player I want to start a game so that I can play checkers with an opponent.
Player Sign-in | As a Player I want to sign-in so that I can play a game of checkers.

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Fail | MG;Oct 15 18; The Sprint I version did not have sign out feature. | Pass | PD;Nov 5 18
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | MG;Oct 15 18 | Pass | PD;Nov 5 18
As a player I want to have the ability to sign-out so nobody can impose as me on the computer. | Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) |  |  | Pass | JR;Nov 5 18
| Given that I am signed-in when I do click on the sign-out link then I expect to be taken to the Home page, now being signed out. |  |  | Pass | JR;Nov 5 18
As a player I want to be able to make a single move when there is an available move. | Given that it is my turn when I make a move then I expect to have valid moves directly in front of my piece to either side. |  |  | Pass | PD;Nov 5 18
| Given that there is a jump move available when I make a move I expect to be forced to make that jump move. |  |  | Pass | PD;Nov 5 18
| Given that I move my piece when I jump the opponents piece then I expect my piece to move and the opponent to loose their checkers piece. |  |  | Pass | PD;Nov 5 18
| Given that I only have a normal piece when I make a move I expect to not be able to move backwards. |  |  | Pass | PD;Nov 5 18
As a player I want to be able to make a double move so I can win the game faster by claiming two pieces. | Given SOME when I have a double jump move available when make the checkers move then I expect my piece to move and the opponent to loose more than 1 piece. |  |  | Pass | PD;Nov 5 18
| Given that I have staged a double jump move, when I backup my move then I expect only my last move to be reverted. |  |  | Pass | PD;Nov 5 18
| Given that I am in the middle of a jump move and have another jump available then I expect to be forced to make it. |  |  | Pass | PD;Nov 5 18
As a player I want to be able move my king piece in either direction and choose when to take a jump, to help me with the game. | Given that I have a valid checkers piece when I reach the other side of the board then I expect to get a king piece. |  |  | Pass | PD;Nov 5 18
| Given that I have a king piece when I move my piece I expect to be able to move in both directions. |  |  | Pass | PD;Nov 5 18
As a new player I want to view helpful hints so that I can get better at the game. | **Given** I'm in the middle of a game **when** I click the help button **then** I recommend tile to flash. |  |  |  |  | Pass | PD; Nov 15 18
| **Given** that I click help **when** help is displayed **then** I expect the help to be for valid moves. |  |  |  |  | Pass | PD; Nov 15 18
| **Given** I click help **when** help is displayed **then** I expect a jump move to be displayed if there is one available. |  |  |  |  | Pass | PD; Nov 15 18
As a player I want the ability to play against the computer so that I don’t have to wait on the other user. | **Given** that I am on the player lobby page **when** I click play with AI **then** I expect to be sent to a game with an AI player. |  |  |  |  | Pass | SC; Nov 25 18
| **Given** I am in a game with an AI player **when** I it is the AI player's turn **then** I expect the AI player to make a logical move. |  |  |  |  | Pass | SC; Nov 25 18
As a player I want to be able to forfeit the game to save my time in a losing situation. | **Given** I am playing against my opponent **when** I see an inevitable loss, **then** I should see a button to forfeit the game.* |  |  |  |  | Pass | SC; Nov 25 18
| **Given** I press the forfeit button **when** I have decided to forfeit, **then** my opponent should grab the W and I should lose. |  |  |  |  | Pass | SC; Nov 25 18
| **Given** I have forfeited **when** I have pressed the forfeit button, **then** I should be taken back to the home page. |  |  |  |  | Pass | SC; Nov 25 18
As a player I want to lose the game if I have zero pieces to comply with rules and save the other player time. | Given I am playing against my opponent when I lost I should see the game end, taking me back to the home page |  |  |  |  | Pass | SC; Nov 25 18
| Given I am playing against my opponent when I win I should see the game end, taking me back to the home page |  |  |  |  | Pass | SC; Nov 25 18
As a player I want to play a bug free game so that I can not get confused while playing. | **Given** I try to log in with non alpha numeric values **when** I click log in **then** I EXPECT the username to be rejected. |  |  |  |  | Pass | SC; Nov 25 18
| Given that I selected an invalid user to play a game with when I get displayed the error message, I expect to be taken to the home page. |  |  |  |  | Pass | SC; Nov 25 18